## Programme
|  | October | [27 empty] | November | [27 empty] | December | [27 empty] | January
Activity | Task Assignment | 2013-10-07 | [6 empty] | 2013-10-14 | [6 empty] | 2013-10-21 | [6 empty] | 2013-10-28 | [6 empty] | 2013-11-04 | [6 empty] | 2013-11-11 | [6 empty] | 2013-11-18 | [6 empty] | 2013-11-25 | [6 empty] | 2013-12-02 | [6 empty] | 2013-12-09 | [6 empty] | 2013-12-16 | [6 empty] | 2013-12-23 | [6 empty] | 2014-01-06 | [6 empty] | 2014-01-13 | [6 empty] | 2014-01-20 | [6 empty] | 2014-01-27
|  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Complete Feasibility Study and Business Plan | Westar | bar: 2013-10-21 M to 2013-12-09 S
Complete Technical Report | Client | bar: 2013-10-21 M to 2013-11-25 S
Complete Environmental Report | Client | bar: 2013-10-21 M to 2013-11-25 S
Certify the Project with Independent Engineer | Independent Engineer | bar: 2013-11-18 M to 2013-12-23 S
Apply for financing and obtain conditional letter of commitment | Client | bar: 2013-12-02 M to 2014-01-27 S
Complete bank loan analysis | Lender | bar: 2014-01-06 M to 2014-01-27 S
Complete Application Package | Client | bar: 2013-10-21 M to 2014-01-27 S
Submit to USDA | Lender | bar: 2014-01-27 M to 2014-01-27 S